## Sheet1
Activity_id | Activity No. | Activity | Time (in Hours)
1 | 1 | Inception | 0
2 | 1.1 | Finalizing Idea | 0
3 | 1.1.1 | Identifying merits and demerits of the Idea | 6
4 | 1.1.2 | Identifying market requirements | 72
5 | 1.1.3 | Getting Approval for the Idea | 2
6 | 1.2 | Planning and Analysis | 0
7 | 1.2.1 | Cost Analysis | 4
8 | 1.2.2 | Resource Analysis | 3
9 | 1.2.3 | Feasibility Study
10 | 1.2.3.1 | Technical Feasibility | 2
11 | 1.2.3.2 | Ecomomic Feasibility | 2
12 | 1.2.3.3 | Legal Feasibility | 24
13 | 1.2.3.4 | Operational Feasibility | 4
14 | 1.3 | Reporting and Updating Team
15 | 1.3.1 | Generating Report | 2
16 | 1.3.2 | Presenting it to Project Manager | 24
17 | 1.3.3 | Getting Approval | 36
18 | 1.3.4 | Updating Team | 1
19 | 2 | Design
20 | 2.1 | Deciding the Platforms
21 | 2.1.1 | Choosing the platform | 24
22 | 2.1.2 | Checking app compatibility for the platform | 5
23 | 2.1.3 | Getting approval from the Project Manager | 1
24 | 2.2 | Developing UX
25 | 2.2.1 | Analysing current trendy themes | 36
26 | 2.2.2 | choosing a way of presenting | 24
27 | 2.2.3 | developing User Experience Techniques | 60
28 | 2.2.4 | Getting approval from the Project Manager | 2
29 | 2.3 | Developing UI
30 | 2.3.1 | Deciding the Activities | 90
31 | 2.3.2 | Creating UI using Designing Softwares | 10
32 | 2.3.3 | Getting UI's Approved | 10
33 | 2.3.4 | Creating the UI on the Application | 160
34 | 2.3.5 | Finalizing the UI Designs asper Platforms | 5
35 | 2.3.6 | Updating Team | 1
36 | 3 | Development
37 | 3.1 | Developing Backend
38 | 3.1.1 | Deciding Databases | 24
39 | 3.1.2 | Connecting Database with the application | 20
40 | 3.2 | Developing the Application
41 | 3.2.1 | Coding | 960
42 | 3.2.2 | Approving the Code Structure | 24
43 | 3.2.3 | Finalizing Codes | 36
44 | 3.2.4 | Exporting Application | 5
45 | 4 | Testing
46 | 4.1 | Unit Testing | 40
47 | 4.2 | Integration Testing | 20
48 | 4.3 | Application Testing (system testing) | 20
49 | 4.4 | Report Generation
50 | 4.4.1 | Test Reports Generation | 3
51 | 4.4.2 | Graphical Representation of the Reports | 2
52 | 4.5 | Submitting Reports to the Team | 1
53 | 4.6 | Updating Team | 1
54 | 5 | Deployment
55 | 5.1 | Releasing Prototype | 1
56 | 5.2 | Generating Report | 5
57 | 5.3 | Releasing Beta Version | 36
58 | 5.4 | Generating Report | 5
59 | 5.5 | Releasing Final Version of the App | 100
60 | 5.6 | Report Generation | 5
61 | 5.7 | Updating Team | 1
62 | 6 | Releasing Application on Stores
63 | 6.1 | Deploying App on App Store | 3
64 | 6.2 | Deploying App on Play Store | 3
65 | 6.3 | Deploying App on Windows Phone Store | 3
66 | 6.4 | Updating Team | 1
67 | 6 | Project Handover and Closure
68 | 6.1 | Handovering project to desired team | 5
69 | 6.2 | Generating working reports | 24
70 | 6.3 | Generating Project Report | 24
71 | 6.4 | Closure of the Project | 3